## Product Backlog
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort
1 | Data Loading & Alignment | Preprocessing | As a researcher, I want to load and align two Copernicus CMEMS NetCDF datasets so that temporal synchronization is ensured. | Must | Completed | 1. Both datasets loaded without error. 2. Time dimensions aligned (1,190 days). 3. NaN values handled (land masking). | Load thetao and SST anomaly NetCDF files using xarray. | Loading time < 2 min; memory < 4 GB. | 2 Days | 2 Days
2 | Min-Max Normalization | Preprocessing | As a developer, I want to normalize SST grids to [0,1] range so that ResNet101 receives properly scaled inputs. | Must | Completed | 1. All values in [0,1] range. 2. Global min/max used (not per-sample). | Apply Min-Max scaling across all time steps and pixels. | Zero data loss; reversible transformation. | 1 Day | 1 Day
3 | RGB Tensor Mapping | Preprocessing | As a developer, I want to encode 3-day temporal windows as RGB channels so the CNN can detect temporal dynamics as spatial gradients. | Must | Completed | 1. Output shape (N, 238, 268, 3). 2. Day T-2=Red, T-1=Green, T=Blue. 3. Sliding window correctly aligned. | Create 3-day sliding window and stack as color channels. | Memory efficient; no data leakage between windows. | 2 Days | 2 Days
4 | RF Feature Engineering | Preprocessing | As a researcher, I want 41 statistical features per sample instead of raw pixels so RF gets meaningful inputs. | Must | Completed | 1. 41 features computed per sample. 2. Features include spatial stats, deltas, gradients, acceleration. 3. No NaN/inf values. | Compute per-day stats, temporal deltas, spatial gradients, acceleration for 3-day windows. | Feature computation < 30s for full dataset. | 3 Days | 3 Days
5 | Cost-Sensitive Oversampling | Preprocessing | As a researcher, I want to oversample top 10% extreme events with noise injection so the model learns rare spikes. | Must | Completed | 1. 90th percentile threshold computed. 2. Extreme events duplicated 3x. 3. Gaussian noise (sigma=0.005) added. 4. Data shuffled. | Identify extremes, duplicate with noise, concatenate and shuffle. | Augmented size ~1,230 samples. | 2 Days | 2 Days
6 | ResNet101 CNN Training | Modeling | As a developer, I want to train ResNet101 with fine-tuned last 20 layers and MSE loss to predict anomalies. | Must | Completed | 1. Val MAE < 0.12C. 2. EarlyStopping triggers. 3. Model saved to Drive. | Load pretrained ResNet101, unfreeze last 20 layers, train with MSE + Adam. | Training < 5 min on T4 GPU. | 5 Days | 4 Days
7 | Random Forest Training | Modeling | As a researcher, I want to train RF on 41 engineered features to capture statistical anomaly patterns. | Must | Completed | 1. 500 trees trained. 2. Spike MAE < 0.07C. 3. Model saved to Drive. | Train RandomForestRegressor with 500 estimators, unlimited depth. | Training < 1 min on CPU. | 2 Days | 1 Day
8 | Ensemble Fusion | Modeling | As a researcher, I want an optimized weighted ensemble combining CNN and RF to beat both individual models. | Must | Completed | 1. Grid search over 0-100% weights. 2. Ensemble MAE < both individual MAEs. 3. Optimal weights documented. | Grid search for optimal CNN-RF weight combination. | Ensemble MAE = 0.0700C (target: < 0.08C). | 3 Days | 3 Days
9 | Comprehensive Evaluation | Validation | As a researcher, I want MAE, RMSE, Spike MAE, Accuracy, F1, confusion matrices for all models. | Must | Completed | 1. All metrics computed for CNN, RF, Ensemble. 2. Spike MAE on top 10%. 3. Classification metrics at 75th percentile. | Compute regression and classification metrics on test set. | Results reproducible with saved models. | 2 Days | 2 Days
10 | MLP Baseline | Validation | As a researcher, I want an MLP baseline to prove CNN spatial convolutions are necessary. | Should | Completed | 1. MLP trained on flattened grid (191,352 features). 2. MLP MAE significantly worse than CNN. | Train 3-layer MLP on flattened RGB tensors. | MLP MAE = 2.587C (37x worse than CNN). | 1 Day | 1 Day
11 | Publication Visualizations | Documentation | As a researcher, I want publication-grade plots for the research paper and review presentation. | Must | Completed | 1. At least 5 publication-quality figures. 2. Saved to Drive at 300 DPI. | Generate time-series, confusion matrices, feature importance, weight sensitivity plots. | All plots at 300 DPI; consistent styling. | 2 Days | 2 Days
12 | Research Paper | Documentation | As a researcher, I want a complete IEEE-format research paper with methodology and results. | Must | Completed | 1. Abstract, Introduction, Related Work, Methodology, Results, Conclusion. 2. All tables and figures referenced. | Write complete research paper in IEEE format. | IEEE formatting guidelines followed. | 5 Days | 5 Days

## Functional Test Cases
Feature | Test Case | Steps to Execute | Expected Output | Actual Output | Status | Notes
Data Loading | Load NetCDF files from Drive | 1. Mount Google Drive 2. Load both .nc files using xarray 3. Check dimensions | Two datasets loaded with matching lat/lon grids | Both datasets loaded: 1296 and 1190 time steps, aligned to 1190 | Pass | Files ~600MB total
Data Alignment | Temporal synchronization | 1. Run xr.align() on both datasets 2. Verify time dimensions match | Both datasets have identical time coordinates | 1,190 synchronized time steps confirmed | Pass
Normalization | Min-Max scaling to [0,1] | 1. Compute global min/max 2. Apply normalization 3. Verify output range | All values in [0.0, 1.0] | Output range: [0.0000, 1.0000]. Min=0K, Max=33.39K | Pass | Global scaling preserves relationships
RGB Tensor | 3-day sliding window creation | 1. Create sliding windows 2. Stack as RGB channels 3. Verify shape | Output shape: (N, 238, 268, 3) | Shape: (1187, 238, 268, 3). Channels correctly mapped. | Pass
RF Features | 41 feature engineering | 1. Compute per-day stats 2. Compute deltas and gradients 3. Verify no NaN | 41 features per sample, no NaN values | Shape: (1187, 41). Zero NaN confirmed. | Pass | Computation time: 20s
Augmentation | Cost-sensitive oversampling | 1. Find 90th percentile threshold 2. Oversample 3x with noise 3. Shuffle | Training size increases by ~30% | Original: 949, Augmented: 1234 (+30%) | Pass | sigma=0.005 noise
CNN Training | ResNet101 training with MSE | 1. Build model 2. Train with augmented data 3. Check val_MAE | Val MAE < 0.12C, EarlyStopping triggers | Best val_MAE = 0.1037C at epoch 5. Stopped at epoch 10. | Pass | Training time: 2.7 min
RF Training | Random Forest on 41 features | 1. Clean NaN/inf 2. Train 500 trees 3. Evaluate | Training completes, Spike MAE < 0.07C | Spike MAE = 0.0589C. Training: 6 seconds. | Pass
Ensemble | Weighted average optimization | 1. Grid search weights 0-1 2. Find minimum MAE 3. Apply optimal weights | Ensemble MAE < both individual models | Optimal: 61% CNN + 39% RF. MAE = 0.0700C | Pass | 30.45% better than CNN alone
Spike Detection | Extreme event accuracy | 1. Identify top 10% spikes in test set 2. Compute Spike MAE for each model | RF catches spikes better than CNN | CNN Spike: 0.2089, RF Spike: 0.0589, Ensemble: 0.1114 | Pass | Complementarity confirmed
MLP Baseline | Standard ML comparison | 1. Flatten RGB tensors 2. Train MLP 3. Compare MAE | MLP significantly worse than CNN | MLP MAE = 2.587C (37x worse). CNN spatial processing essential. | Pass
Model Save | Checkpoint to Google Drive | 1. Save CNN (.keras) 2. Save RF (.joblib) 3. Save ensemble config | All models saved and loadable | All 3 models saved to Drive/Minor project/models/ | Pass | Model locked, no retraining